## Archer (hidden)
Maintenance Update - June 2017 - As of 6/26
Application | Work Items Completed | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
ARCHER - AC DAMAGE | 0 | 1 | 0 | 0 | validated works as designed with archer upgrade v6.2 | pending resolution of ac damage Web service issue with cers field transferring adata to archer
ARCHER - INJURY INVESTIGATIONS | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - SSE EVENTS | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - USCBP FINES | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - DEPORTEES | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - IIR | 0 | 0 | 2 | 0 | validated works as designed with archer upgrade v6.2 | • update user guide post archer upgrade v 6.2 • spike for solution for group profiles
ARCHER - AADVANATAGE FRAUD | 0 | 1 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - GLOBAL INVESTIGATIONS | 4 | 1 | 5 | 4 | validated works as designed with archer upgrade v6.2 | pending estimates on new work for determination of eligibility of maint/ small enhancement or if need to move foprward as new project(s).
ARCHER - ENABLON – REVENUE PROTECTION/RECOVERY | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - OSHA ACTIVITY REPORTING | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - LAW ENFORCEMENT LOG | 0 | 0 | 1 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - REVENUE PROTECTION/RECOVERY | 0 | 1 | 1 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - SECURITY OPERATIONS | 0 | 1 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
ARCHER - CORPORATE SECURITY INVESTIGATIVE REPORT - NOTES | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
Environmental - 3E | 0 | 0 | 0 | 0 | validated works as designed with archer upgrade v6.2 | n/a
Environmental -OPS | 0 | 0 | 0 | 3 | validated works as designed with archer upgrade v6.2 | n/a
Environmental -ADWR/AEDWR | 0 | 0 | 0 | 18 | validated works as designed with archer upgrade v6.2 | maint on hold for safety server refersh project.

## Security
Maintenance Update - March 2018 - As of 3/23
Application | Work Items Completed | Avg Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
Security - BPA | 10 | 3 | 14 | 10 | 76 | Project Spring Sign off | Replacing SAM to Initiate a Badge request
Security - BMA | 1 | 6 | 3 | 1 | 18 | Nightly batch process to update employee as Active/Inactive. | Ability to update location with a nightly batch
Security - KCM | 5 | 1 | 1 | 7 | 42 | Project Spring Sign off | Automation of the TSA Internal Audit
Security.aa.com | 2 | 3 | 4 | 2 | 26 | Project Spring Sign Off | Move over to new VM

## CERS
CERS Maintenance Update - April 2018 (As of 4/20/18)
Application | Work Items Completed | Avg Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
Legacy CERS - WEB | 10 | 12 days | 3 | 6 | 4 |  | • Continue to work on minor changes and production defects.
CERS - WEB (New) | 0 | 0 | 0 | 1 | 2 |  | • Revise web and service tier runbooks. • Support transition of Pilot Event Report features for report detail and history to production.
CERS - Mobile | 6 | 36 days | 1 | 5 | 13 | • Deployed CERS Mobile alpha production release for FACET and completed alpha validation. | • Continue work to support the CERS mobile beta and production rollout to FACET devices. • Continue to support Pilot Event Report mobile alpha and beta production releases.
CERS - Services | 18 | 7 days | 6 | 18 | 20 | • Closed all post-cutover defects associated with the Project Spring cutover. | • Complete the consolidation of CERS report notification delivery through message server. Plan to deploy by end of month.
CERS- Client | 4 | 3 days | 3 | 16 | 7
* Maintenance team continues to refine work items for the Q2 Release Backlog. * Extended "Avg Age of Completed Items" for some due to CERS Maintenance resources support of both Pilot Event Reporting (P2 Replacement) and Project Spring.

## EtQ
Maintenance Update - 2/26 to 3/23
Application | Work Items Completed | Avg Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
ETQ - Reg Compliance | 3 | 16 | 2 | 1 | 8 |  | Overall Status is Green with only small stories in the backlog.
ETQ - OSH Audit | 1 | 67 | 2 | 0 | 6 |  | Business submitted BTR for OSH Self Audit and is working on Second BTR for Mobile Applications. Creating stories for Cognos Reporting
ETQ - Dangerous Goods | 2 | 17 | 1 | 1 | 7 |  | Business needs to make major change to workflow for Legal Compliance, and there is a story (US751837) for data import. Requesting PO submit BTR for both.
ETQ - Corp Security | 0 | N/A | 3 | 0 | 16 |  | Looking at new option provided by Ashish Aryal to lock down CSC module. This has been an ongoing issue.
ETQ - CCQ Inspections | 0 | N/A | 0 | 1 | 7 |  | James Jeffers has taken over CCQ as the PO. There are no outstanding issues at this time.
ETQ - Winter Operations | 1 | Story was on hold for ChangeFreeze | 5 | 4 | 4 |  | Issue found with Task sequences that rollback the SDP Forms for the New Season. The functions performed by the Tasks conflict with the original design of the application. Temp fix in production, needs to be fixed before next season.
ETQ - IOSA | 0 | N/A | 0 | 0 | 0 |  | Meeting next week to discuss next upload of IATA questions.
This does not include admin changes recorded in TEAM - ETQ Reliance SSE Maintenance Queue (Adding users, user groups, locations, task profiles, etc.)

## Archer_Safety
Maintenance Update - July 2017 - As of 7/24
Application | Work Items Completed | Average Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
ARCHER - AC DAMAGE | 1 | 15 days | 0 | 0 | 0 | n/a | resolved ac damage Web service issue with cers field transferring a data to archer
ARCHER - INJURY INVESTIGATIONS | 0 |  | 0 | 0 | 0 | n/a | n/a
ARCHER - OSHA ACTIVITY REPORTING | 0 |  | 0 | 0 | 0 | n/a | n/a
ARCHER - SSE Events | 0 |  | 0 | 0 | 0 | n/a | n/a
Environmental - 3E | 0 |  | 0 | 0 | 0 | n/a | pending backlog grooming to review old requests, create new work and prioritize work
Environmental -OPS | 0 |  | 0 | 0 | 5 | n/a | pending backlog grooming to review old requests, create new work and prioritize work
Environmental -ADWR/AEDWR | 0 |  | 0 | 0 | 16 | Upgrade to new environment completed removing block for future maintenance work | pending backlog grooming to review old requests, create new work and prioritize post Safety Server refersh project

## Environmental & Safety
Maintenance Update - July 2017 - As of 7/24
Application | Work Items Completed | Average Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
CEFA | 1 | 15 days | 0 | 0 | 0 | n/a | resolved ac damage Web service issue with cers field transferring a data to archer
ARCHER - INJURY INVESTIGATIONS | 0 |  | 0 | 0 | 0 | n/a | n/a
ARCHER - OSHA ACTIVITY REPORTING | 0 |  | 0 | 0 | 0 | n/a | n/a
ARCHER - SSE Events | 0 |  | 0 | 0 | 0 | n/a | n/a
Environmental - 3E | 0 |  | 0 | 0 | 0 | n/a | pending backlog grooming to review old requests, create new work and prioritize work
Environmental -OPS | 0 |  | 0 | 0 | 5 | n/a | pending backlog grooming to review old requests, create new work and prioritize work
Environmental -ADWR/AEDWR | 0 |  | 0 | 0 | 16 | Upgrade to new environment completed removing block for future maintenance work | pending backlog grooming to review old requests, create new work and prioritize post Safety Server refersh project

## EP&R
Maintenance Update - July 2017 - As of 7/24
Application | Work Items Completed | Avg Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities

## SSE General Apps
Maintenance Update - March 2018 - 3/23
Application | Work Items Completed | Avg Age of Completed Items | Work Items in Progress | Release Backlog | Unscheduled Backlog | Major Accomplishments | Overall Status / Upcoming Activities
AGS Uploader | 3 |  | 1 |  |  | AGS uploader working succcessfully on new quntum machines loctaed at DCA (Center Pier) and SEA. | Working with Desktop team to install AGS uploader on quntum machine located at DCA North Pier Techops. Need to submit a FAR for DCA.
WBAT | 1 |  |  |  |  | Updated our signing certificate for WBAT AA and WBAT Envoy.
CEFA |  |  | 1 |  |  |  | Working with Quntum to get the new version of CEFA-FAS v2.5.42 Quntum certified.
FRMS | 2 |  |  |  |  | Migrated the data to the production so that BU can do the thorough analysis of data.
EFOQA | 1 |  | 2 |  |  |  | Pending tickets with GE related to Training, config changes.