## Sheet1
Project: Hydra Server: dev.azure.com/cloudideaas Query: Backlog Tree List type: Tree
ID | Work Item Type | Original Estimate | Remaining Work | Title 1 | Title 2 | Title 3 | Title 4 | Title 5 | Title 6 | Title 7 | Title 8 | Title 9 | Assigned To | State | Tags
8 | Epic |  |  | Title 1: Hydra Application - Workable Demo Phase 1 |  | New
9 | Feature |  |  | Title 2: Initial Generation |  | New
12 | Feature |  |  | Title 3: DevOps Project Generation |  | New
10 | User Story |  |  | Title 4: Creation of GitHub Repository |  | New
24 | User Story |  |  | Title 5: Creation of Temporary Local Workspace |  | New
25 | User Story |  |  | Title 5: Creation of Config.json |  | New
27 | Task |  |  | Title 6: Call npm init on app folder |  | New
26 | User Story |  |  | Title 5: Creation of Repository |  | New
28 | Task |  |  | Title 6: Develop hydra generate repository --name [name] |  | New
29 | Task |  |  | Title 6: Commit and push |  | New
11 | User Story |  |  | Title 4: Creation of DevOps Project Framework |  | New
30 | User Story |  |  | Title 5: Creation of DevOps project |  | New
31 | User Story |  |  | Title 5: Creation of Azure Web application |  | New
32 | User Story |  |  | Title 5: Creation of DevOps build definition |  | New
33 | User Story |  |  | Title 5: Creation of DevOps release definitions |  | New
34 | User Story |  |  | Title 5: Creation of user stories for boiler plate application |  | New
35 | User Story |  |  | Title 5: Creation of of dashboard page for Business Model |  | New
36 | User Story |  |  | Title 6: Creation of dashboard |  | New
37 | User Story |  |  | Title 6: Creation of embedded widget |  | New
13 | User Story |  |  | Title 4: RestAbstraXProvider Functionality |  | New
16 | User Story |  |  | Title 5: Query Provider |  | New
17 | User Story |  |  | Title 5: JSON Input File for DevOps |  | New
19 | User Story |  |  | Title 6: WorkItems |  | New
65 | Task | 24 | 24 | Title 7: WorkItems |  | New
66 | Task | 4 | 4 | Title 7: CastTo Functionality |  | New
67 | Task | 4 | 4 | Title 7: WorkItem |  | New
68 | Task | 8 | 8 | Title 7: Fields |  | New
69 | Task | 4 | 4 | Title 7: Field |  | New
70 | User Story |  |  | Title 6: Boards |  | Removed
71 | Task |  |  | Title 7: Board |  | Removed
72 | Task |  |  | Title 7: Columns |  | Removed
73 | Task |  |  | Title 7: Rows |  | Removed
74 | User Story |  |  | Title 6: Dashboard |  | New
75 | Task | 4 | 4 | Title 7: Dashboard |  | New
76 | Task | 6 | 6 | Title 7: Dashboards |  | New
77 | Task | 8 | 8 | Title 7: GroupEntries |  | New
78 | Task | 16 | 16 | Title 7: DashboardGroupEntry |  | New
79 | User Story |  |  | Title 6: Build |  | New
81 | Task | 4 | 4 | Title 7: YAML Generation |  | New
195 | Task | 4 | 4 | Title 7: az pipelines create |  | New
82 | User Story |  |  | Title 6: Release |  | New
84 | Task | 4 | 4 | Title 7: Figure out releases |  | New
196 | Task | 1 | 1 | Title 7: YAML Generation |  | New
197 | Task | 1 | 1 | Title 7: az pipelines create |  | New
18 | User Story |  |  | Title 5: AbstraXProvider Generator |  | New
21 | User Story |  |  | Title 6: Basic Functionality | ken.l.netherland | Active
61 | Bug | 3 | 0 | Title 7: Resolve missing facet for WorkItems | ken.l.netherland | Resolved
86 | Task | 4 | 0 | Title 7: Finish code generation for RESTful provider | ken.l.netherland | Active
89 | Task | 3 | 0 | Title 7: Finish Code generation for file types | ken.l.netherland | Active
90 | Bug | 2 | 0 | Title 7: Stack empty on WorkItemReference ( "Handlers: 'WebAPIModelFacetHandler, WebAPIControllerFacetHandler'" ) | ken.l.netherland | Resolved
95 | Test Case |  |  | Title 7: Architect has the ability to run the HydraCLI without errors | ken.l.netherland | Design
100 | Test Case |  |  | Title 7: The following code files should be created per container: GraphQLSchema (named HydraDevOps.Services\GraphQL\[Name]Schema.cs) | ken.l.netherland | Design
101 | Test Case |  |  | Title 7: The following code files should be created per project: StartupSchemas (named HydraDevOps.Services\GraphQL\StartupSchemas.cs) | ken.l.netherland | Design
102 | Test Case |  |  | Title 7: The following code files should be created per container: Query (named HydraDevOps.Services\GraphQL\[Name]Query.cs) | ken.l.netherland | Design
103 | Test Case |  |  | Title 7: The Query should include one Field per Entity | ken.l.netherland | Design
104 | Test Case |  |  | Title 7: The following code files should be created per *.Model.json (i.e. Ripley.Entities\AzureDevOps\AzureDevOps.Model.json) | ken.l.netherland | Design
105 | Test Case |  |  | Title 7: The following code files should be created per Entity | ken.l.netherland | Design
22 | User Story |  |  | Title 6: GraphQL | ken.l.netherland | Active
62 | Task | 2 | 0 | Title 7: Finish QueryProvider added methods for GraphQL | ken.l.netherland | Active
63 | Task | 2 | 0 | Title 7: GraphQL preprocessing | ken.l.netherland | Active
23 | User Story |  |  | Title 6: Restful Parenting of Entity |  | Active
64 | Task | 100 | 0 | Title 7: Creation of LINQ query for parent of Projects |  | Active
85 | User Story |  |  | Title 6: Set up Environment for Testing (Phase 1) | ken.l.netherland | Active
87 | Task | 3 | 0 | Title 7: Deploy HydraCLI | ken.l.netherland | Removed
134 | Task |  |  | Title 8: Placeholder (Repeat tasks from Sample App) | ken.l.netherland | Removed
88 | Task | 5 | 5 | Title 7: Deploy HydraDevOps Service | ken.l.netherland | Removed
135 | Task |  |  | Title 8: Placeholder (Repeat tasks from Sample App) |  | Removed
97 | Bug | 4 | 0 | Title 7: Process 'msbuild.exe' exited with code '1' | ken.l.netherland | Resolved
106 | User Story |  |  | Title 7: Initial Steps (Manual Deployment) |  | Active
107 | User Story |  |  | Title 8: Sample App |  | Active
109 | Task | 1 | 0 | Title 9: Install Docker registry | ken.l.netherland | Active
110 | Task | 4 | 0 | Title 9: Create a Dockerfile | ken.l.netherland | Active
111 | Task | 4 | 0 | Title 9: Create a local Docker image | ken.l.netherland | Active
112 | Task | 1 | 0 | Title 9: Publish image to Docker registry | ken.l.netherland | Active
113 | Task | 1 | 0 | Title 9: Install Docker on Virtual server | ken.l.netherland | Removed
114 | Task | 4 | 0 | Title 9: Create a Swarm | ken.l.netherland | Active
115 | Task | 1 | 0 | Title 9: Install from registry on Swarm | ken.l.netherland | Active
116 | Task | 2 | 0 | Title 9: Run Swarm container from local machine | ken.l.netherland | Active
136 | User Story |  |  | Title 5: Set up Environment for Testing (Phase 2) |  | Active
137 | User Story |  |  | Title 6: Initial Steps |  | Active
138 | User Story |  |  | Title 7: Sample App |  | Active
108 | Task | 100 | 0 | Title 8: Reinstall Kubernetes (view video for preferences) | ken.l.netherland | Active
117 | Task | 3 | 0 | Title 8: Use kubectl to configure | ken.l.netherland | Active
118 | Task | 2 | 0 | Title 8: Use kubectl to install from registry | ken.l.netherland | Active
119 | Task |  | 0 | Title 8: Run Azure Kubernetes Service (AKS) container from local machine | ken.l.netherland | Removed
120 | Task | 1 | 0 | Title 8: Install Helm client | ken.l.netherland | Active
121 | Task | 1 | 0 | Title 8: Install Helm on AKS | ken.l.netherland | Active
122 | Task | 3 | 0 | Title 8: Configure RBAC and TLS | ken.l.netherland | Active
123 | Task |  | 0 | Title 8: Test Helm client connect to Tiller on AKS | ken.l.netherland | Removed
124 | Task | 12 | 0 | Title 8: Create a Helm chart | ken.l.netherland | Active
125 | Task | 4 | 0 | Title 8: Create chart tests | ken.l.netherland | Active
126 | Task | 4 | 0 | Title 8: Package chart | ken.l.netherland | Active
127 | Task | 16 | 0 | Title 8: Push package to AKS | ken.l.netherland | Active
128 | Task |  | 0 | Title 8: Run Azure Kubernetes Service (AKS) container from local machine | ken.l.netherland | Removed
129 | Task | 1 | 0 | Title 8: Do a Helm upgrade and release | ken.l.netherland | Active
130 | Task | 230 | 0 | Title 8: Set up CI pipeline | ken.l.netherland | Active
131 | Task | 20 | 0 | Title 8: Set up CD pipeline | ken.l.netherland | Active
132 | Task | 4 | 0 | Title 8: Create a Dev Space for developer testing | ken.l.netherland | Active
133 | Task |  | 0 | Title 8: Run Azure Kubernetes Service (AKS) container from local machine | ken.l.netherland | Removed
139 | Task | 100 | 0 | Title 8: Set up an Azure Resource Manager Template for Kubernetes install | ken.l.netherland | Active
140 | User Story |  |  | Title 7: Deploy Hydra DevOps service |  | Active
141 | Task | 8 | 0 | Title 8: Reinstall Kubernetes using ARM template |  | Active
142 | Task | 2 | 4 | Title 8: Deploy and Test |  | Active
143 | User Story |  |  | Title 7: Deploy HydraCLI |  | Active
144 | Task | 2 | 0 | Title 8: Reinstall Kubernetes using ARM template |  | Active
145 | Task | 4 | 8 | Title 8: Deploy and Test |  | Active
146 | Task | 8 | 2 | Title 8: Make HydraCLI testable | ken.l.netherland | Active
14 | Feature |  |  | Title 3: Business Model Functionality |  | New
38 | User Story |  |  | Title 4: Creation of boilerplate Business Model hierarchy |  | New
39 | Task |  |  | Title 5: Develop hydra generate businessmodel --dataitems --sample [sample input file] |  | New
15 | Feature |  |  | Title 3: DataItem Functionality |  | New
40 | User Story |  |  | Title 4: Creation of boilerplate Data Items |  | New
148 | Task |  |  | Title 5: Develop hydra generate dataitems --sample [sample input file] |  | New
45 | Feature |  |  | Title 3: Application Code Generation |  | New
46 | User Story |  |  | Title 4: Generation of solution |  | New
47 | Task |  |  | Title 5: Develop hydra generate solution |  | New
48 | User Story |  |  | Title 4: Generation of Entities project |  | New
49 | Task |  |  | Title 5: Develop hydra generate entities |  | New
50 | User Story |  |  | Title 4: Database generation code |  | New
51 | User Story |  |  | Title 4: Mock data in SQLite |  | New
52 | User Story |  |  | Title 4: Commits/pushes solution - kicks of remote generation |  | New
53 | Task |  |  | Title 5: Finish hydra generate app |  | New
41 | Feature |  |  | Title 2: Custom Creation |  | New
42 | Feature |  |  | Title 3: Business Model Editor Functionality |  | New
54 | User Story |  |  | Title 4: Custom properties |  | New
55 | User Story |  |  | Title 4: Mock data |  | New
56 | Task |  |  | Title 5: Mock api |  | New
57 | Task |  |  | Title 5: Mock type in column properties |  | New
58 | Task |  |  | Title 5: Generate data button |  | New
59 | Task |  |  | Title 5: Data editor |  | New
60 | Task |  |  | Title 5: Save to server |  | New
149 | Task |  |  | Title 5: Pull down loates Mock types page from server, including script |  | New
43 | Feature |  |  | Title 3: DataItem Editor Functionality |  | New
150 | User Story |  |  | Title 4: DropPanel |  | New
151 | Task |  |  | Title 5: Make pinnable |  | New
152 | Task |  |  | Title 5: Add status bar |  | New
153 | Task |  |  | Title 5: Add help cabability |  | New
154 | User Story |  |  | Title 4: Related Entity Options |  | New
155 | User Story |  |  | Title 5: Entity Panel |  | New
156 | Task |  |  | Title 6: Get entities from server |  | New
157 | User Story |  |  | Title 5: Is a (one-to-one) |  | New
158 | User Story |  |  | Title 5: Can be a (zero-to-one) |  | New
159 | Task |  |  | Title 6: More criteria methods |  | New
160 | Task |  |  | Title 6: Always No |  | New
161 | Task |  |  | Title 6: Always Yes |  | New
162 | User Story |  |  | Title 5: Contains (x-to-many) |  | New
163 | Task |  |  | Title 6: Lookup No (one-to-many) |  | New
164 | Task |  |  | Title 6: Lookup No (many-to-many) |  | New
165 | User Story |  |  | Title 5: Is Lookup Of (many-to-one) |  | New
166 | User Story |  |  | Title 5: Edit Related |  | New
167 | Task |  |  | Title 6: Pass flag up whether or not created |  | New
168 | Task |  |  | Title 6: Default to 'Create' |  | New
169 | Task |  |  | Title 6: Disable until ready |  | New
44 | Feature |  |  | Title 2: Final Generation |  | New
170 | Feature |  |  | Title 3: Application Admin screens |  | New
171 | User Story |  |  | Title 4: Auto generate lookups |  | New
172 | User Story |  |  | Title 4: Auto generate users, roles, permissions |  | New
173 | User Story |  |  | Title 4: "Login as" functionality |  | New
174 | User Story |  |  | Title 4: Test users |  | New
175 | Task |  |  | Title 5: Prevent login |  | New
176 | Feature |  |  | Title 3: Application Generation |  | New
177 | User Story |  |  | Title 4: Generate solution |  | New
178 | Task |  |  | Title 5: Develop hydra generate solution |  | New
179 | User Story |  |  | Title 4: Generate entities |  | New
180 | Task |  |  | Title 5: Develop hydra generate entities --input:[Input data items file] |  | New
181 | Task |  |  | Title 5: Generates database generation code |  | New
182 | Task |  |  | Title 5: Generates mock data in SQLite |  | New
183 | User Story |  |  | Title 4: Commits/pushes solution - kicks off remote generation |  | New
184 | Task |  |  | Title 5: Finish hydra generate app |  | New
185 | Feature |  |  | Title 3: Basic Functionality |  | New
186 | User Story |  |  | Title 4: Finish install from cache |  | New
187 | User Story |  |  | Title 4: Finish conference sample upgrade |  | New
188 | User Story |  |  | Title 4: Figure out nested menus |  | New
189 | User Story |  |  | Title 4: Determine approach for component stack |  | New
190 | User Story |  |  | Title 4: Finish custom facet handler |  | New
191 | User Story |  |  | Title 4: Generate Grid Dropdown |  | New
91 | Test Plan |  |  | Title 1: Hydra Test Plan | ken.l.netherland | Active
92 | Test Suite |  |  | Title 1: Hydra Test Plan | ken.l.netherland | In Progress
99 | Test Suite |  |  | Title 1: HydraCLI Test Suite | ken.l.netherland | In Progress
192 | Epic |  |  | Title 1: Hydra Application - Workable Demo Phase 2 |  | New
193 | Feature |  |  | Title 2: Data Warehousing Capability |  | New
194 | Feature |  |  | Title 2: Reporting Capability |  | New

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Select User... | Select User... | Active | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Closed | Select User... | Active | Bug | Select User... | Active | Active | Active | Active | Closed | New | Bug | New
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \AzureDevOps | \Iteration 1 | ken.l.netherland | ken.l.netherland | Inactive | Closed | ken.l.netherland | Closed | ken.l.netherland | Closed | ken.l.netherland | Closed | ken.l.netherland | Closed | ken.l.netherland | Design | ken.l.netherland | Closed | Epic | ken.l.netherland | Closed | Closed | Closed | Closed | Design | Removed | Code Review Request | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_EC-0F-7A-13-B7-B8-F1-00-EB-63-A3-B5-07-10-E1-15-11-B0-2B-46
|  |  |  | \HydraCLI | \Iteration 1\Sprint 20.1.1 | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Bug_System.AssignedTo | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_F2-50-E0-0B-A4-70-41-0E-4F-EA-EB-F4-E5-AB-8E-F2-0B-C6-74-F1 | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_24-4F-41-C6-43-F9-7A-F0-22-C5-E5-E8-42-3D-A1-AA-B2-2F-17-7F | New | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Epic_System.AssignedTo | New | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Feature_System.AssignedTo | New | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Issue_System.AssignedTo | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Issue_System.State | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Task_System.AssignedTo | New | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Test Case_System.AssignedTo | Ready | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_User Story_System.AssignedTo | New | Feature | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_System.AssignedTo | New | New | New | New | Ready | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_14-18-8D-4C-27-3A-95-7A-66-EC-9A-D6-EB-E0-78-2D-45-6D-31-D5 | Code Review Response
|  |  |  | \HydraDevOps | \Iteration 1\Sprint 20.1.2 |  |  |  | Resolved |  | Removed |  | Removed |  |  |  | Removed |  | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Test Case_System.State |  | Removed | Issue |  | Resolved | Removed | Removed | Resolved | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_E4-CA-08-0D-C5-01-AB-82-96-6F-B8-39-E9-3E-EA-3F-57-42-86-2A |  | Epic
|  |  |  | \HydraDevOpsServices | \Iteration 1\Sprint 20.1.3 |  |  |  | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Bug_System.State |  | Resolved |  | Resolved |  |  |  | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Task_System.State |  |  |  | Resolved | Task |  | Removed | Resolved | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_D9-65-6F-80-61-94-FF-9D-B2-07-9D-3A-AC-47-E7-8F-20-BA-F6-93 | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_11-6D-5A-E2-7A-C5-F4-6A-92-B3-79-84-3C-6A-FF-8C-4A-72-87-BC |  |  | Feature
|  |  |  | \HydraGenServices | \Iteration 1\Sprint 20.1.4 | [5 empty] | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Epic_System.State |  | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_Feature_System.State | [7 empty] | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_User Story_System.State | Test Case |  | Design | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_40-BC-AA-30-81-E2-8A-00-C4-6A-19-69-9D-98-4F-0C-87-30-E5-EC |  |  |  |  | Feedback Request
|  |  |  | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_System.AreaPath | \Iteration 1\Sprint 20.1.5 | [16 empty] | User Story |  | Ready | [5 empty] | Feedback Response
[5 empty] | \Iteration 1\Sprint 20.1.6 | [16 empty] | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_System.WorkItemType |  | all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_System.State | [5 empty] | Issue
[5 empty] | \Iteration 2 | [24 empty] | Shared Parameter
[5 empty] | \Iteration 2\Sprint 20.2.1 | [24 empty] | Shared Steps
[5 empty] | \Iteration 2\Sprint 20.2.2 | [24 empty] | Task
[5 empty] | \Iteration 2\Sprint 20.2.3 | [24 empty] | Test Case
[5 empty] | \Iteration 2\Sprint 20.2.4 | [24 empty] | Test Plan
[5 empty] | \Iteration 2\Sprint 20.2.5 | [24 empty] | Test Suite
[5 empty] | \Iteration 2\Sprint 20.2.6 | [24 empty] | User Story
[5 empty] | \Iteration 3 | [24 empty] | VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_8A-5E-88-91-F9-33-2C-72-FD-B9-6E-A0-88-69-F8-C9-79-30-EB-BC
\Iteration 3\Sprint 20.3.1
\Iteration 3\Sprint 20.3.2
\Iteration 3\Sprint 20.3.3
\Iteration 3\Sprint 20.3.4
\Iteration 3\Sprint 20.3.5
\Iteration 3\Sprint 20.3.6
\Iteration 4
\Iteration 4\Sprint 20.4.1
\Iteration 4\Sprint 20.4.2
\Iteration 4\Sprint 20.4.3
\Iteration 4\Sprint 20.4.4
\Iteration 4\Sprint 20.4.5
\Iteration 4\Sprint 20.4.6
all_VSTS_278dfb3e_891b_44b5_b2be_b208d0befcf3_System.IterationPath