## Hydra Schedule
Sa | 2019-12-07 | Grooming/Sprint Planning | 1.5 hour | morning |  | M | Tu | W | Th | F
| 2019-12-07 | Review | 30 minutes | evening | Week -4 |  |  | Demo | It Planning
Su | 2019-12-08 | Scrum | 15 minutes |  | Week -3 |  | Retro |  | Grooming
M | 2019-12-09 |  |  |  | Week -2 |  |  | Demo | It Planning
T | 2019-12-10 | Scrum | 15 minutes |  | Week -1 |  | Retro |  | Grooming
W | 2019-12-11
Th | 2019-12-12 | Scrum | 15 minutes |  | Week 1 | Scrum | Scrum | Review | Planning | Scrum
F | 2019-12-13 |  |  |  | Week 2 | Scrum | Retro | Scrum | Grooming | Scrum
Sa | 2019-12-14 | Scrum
Su | 2019-12-15
M | 2019-12-16
T | 2019-12-17 | Scrum | 15 minutes
W | 2019-12-18
Th | 2019-12-19 | Scrum | 15 minutes
F | 2019-12-20
Sa | 2019-12-21 | Grooming/Sprint Planning | 1.5 hour | morning
| 2019-12-21 | Review | 30 minutes | evening

## Jojo TODO
1 | Create gmail account | https://support.google.com/mail/answer/56256?hl=en
2 | Create office account | https://www.office.com/
3 | Schedule ceremonies
4 | View presentation
5 | Schedule overview of Hydra
6 | Log into devops and get familiar | https://dev.azure.com/cloudideaas
7 | Log into github and view documentation | https://github.com/CloudIDEaaS/root

## Schedule
| Iteration |  | Day 1 - 7 | Day 1 | Day 10 | Day 10 + 6 |  | M | Tu | W | Th | F
|  |  | Th - Grooming | Th - Iteration Planning | W - Demo | Tu - Retro | Week -4 |  |  | Demo | It Planning
June | 2018-06-07 | 2018-06-20 | 2018-05-31 | 2018-06-07 | 2018-06-20 | - | Week -3 |  | Retro |  | Grooming
| 2018-06-21 | 2018-07-04 | 2018-06-14 | 2018-06-21 | 2018-07-04 | 2018-07-10 | Week -2 |  |  | Demo | It Planning
July | 2018-07-05 | 2018-07-18 | 2018-06-28 | 2018-07-05 | 2018-07-18 | 2018-07-24 | Week -1 |  | Retro |  | Grooming
| 2018-07-19 | 2018-08-01 | 2018-07-12 | 2018-07-19 | 2018-08-01 | 2018-08-07
Aug | 2018-08-02 | 2018-08-15 | 2018-07-26 | 2018-08-02 | 2018-08-15 | 2018-08-21 | Week 1 | Stand up | Stand up | Demo | It Planning | Stand up
| 2018-08-16 | 2018-08-29 | 2018-08-09 | 2018-08-16 | 2018-08-29 | 2018-09-04 | Week 2 | Stand up | Retro | Stand up | Grooming | Stand up
| 2018-08-30 | 2018-09-12 | 2018-08-23 | 2018-08-30 | 2018-09-12 | 2018-09-18
Sept | 2018-09-13 | 2018-09-26 | 2018-09-06 | 2018-09-13 | 2018-09-26 | 2018-10-02
| 2018-09-27 | 2018-10-10 | 2018-09-20 | 2018-09-27 | 2018-10-10 | 2018-10-16
Oct | 2018-10-11 | 2018-10-24 | 2018-10-04 | 2018-10-11 | 2018-10-24 | 2018-10-30
| 2018-10-25 | 2018-11-07 | 2018-10-18 | 2018-10-25 | 2018-11-07 | 2018-11-13
Nov | 2018-11-08 | 2018-11-21 | 2018-11-01 | 2018-11-08 | 2018-11-21 | 2018-11-27
| 2018-11-22 | 2018-12-05 | 2018-11-15 | 2018-11-22 | 2018-12-05 | 2018-12-11
| 2018-12-06 | 2018-12-19 | 2018-11-29 | 2018-12-06 | 2018-12-19 | 2018-12-25
| 2018-12-20 | 2019-01-02 | 2018-12-13 | 2018-12-20 | 2019-01-02 | 2019-01-08
1900-01-05
Schedule Week 1, Week 2 standups
Schedule ceremonies
Reschedule around holidays
Work around other's calendars
Add agendas
Add WebEx
Add Meeting notes
Add participants
Formulas:
Day 1 - 7 = [Day 1] - 7
Day 1 = [Iteration]
Iteration = [Iteration, row above]+14
Day 10 + 6 = [Day 10]+6

## Sprint Checklist
Ceremony | Role | Task | Target day |  | Expectation/ Outcome | Other
Retro | PM | Advance email for Retros (include the ideaazboard link) | Friday include the link in the invite: http://www.ideaboardz.com | F |  | https://www.bing.com/images/search?view=detailV2&ccid=jWFNA%2b3D&id=888F823931F66AA790EEF353704BE4C8B125B679&thid=OIP.jWFNA-3DnWPCnbrBmKn9RAHaP_&mediaurl=https%3a%2f%2fhighlandliteracy.files.wordpress.com%2f2014%2f10%2fsix_hats_summary_card01.jpg&exph=1382&expw=640&q=six+thinking+hats&simid=608039544756503176&selectedIndex=0&ajaxhist=0
| PM | Agenda item in stand up for retro input | Friday, Monday, mention the retro | F, M
As Needed | BA | New story review | BA to reach out to PO by email with other's copied, or BA to set up a pre-grooming meeting. (see Maintenance Story categories) |  | Tags added for component type. Added to proper backlog or iteration.
As Needed | PM | New story/defect reviewed via Outlook rule | Ken to review for completeness
As Needed | PM | Defect prod | Reach out to get criticality. Assure a defect is created in Rally from Cherwell tickets with the ticket #. |  | Defect created in Rally with Cherwell ticket #
Grooming | BA | BA review | Prior to Pre-grooming |  |  | Answer who, what, when, where, and how?
| BA | Pre-grooming | Prior to Grooming
| BA | Story writing | After Pre-grooming
| BA | Prioritization meeting | Monthly |  |  | Monthly at a minimum or as needed. Kimi to take point
| BA | List of stories for review | Monday before, BA to have list of stories to be reviewed. | M |  | Discussion between BA, PM. Information from Randy, Jeslin of anything that needs to be added to list.
| Team | Grooming ceremony |  |  | Pointed Stories, defects set as Ready. To be pulled into Planning. Assure template tasks are added. Stories/defects are aligned to proper epics. Decomposed development tasks added if possible. | Turn meeting over to BA
Demo | Team |  | Monday before demo, discuss in standup what is coming up. | M | Stories, Defects, Spikes are accepted or updated for further clarification | By next demo, have a good case for developers for doing them
| PM | List of demo items in meeting invite | Include list in demo meeting invite by Tuesday. | T
Sprint Planning | PM | Agenda item in stand ups to look for groomed stories that need to be tasked. Follow up emails as last resort. | Discuss adding decomposed tasks to stories starting the Monday of planning | M | Decomposed tasks are added to stories or an ETA as to when they will be added