## Sheet1
Visit for Story Components: | http://wiki.horizon.qcorpaa.aa.com/pages/viewpage.action?spaceKey=SSEC&title=User+story+-+the+pieces+needed
Work Item Categories (Stories, Defects) | Definition, Criteria | Next Steps | Activities/Ceremonies | Backlog Location
New - Undocumented | Unclear of component affected, unclear of who should be assigned (gap or enhancement) | BA to reach out to PO by email with other's copied, or BA to set up a pre-grooming meeting | Pre-grooming | Anywhere
User Requirement | Has all of the criteria in link above (minus tasks or story points) | Grooming needs to occur for pointing. Can include tasking if time allowed or will be assigned to developer to task | Grooming | Below the green line or newly required in the current iteration
New User Requirement - Unplanned | Enhancement (scope creep) | BA to email with other's copy or set up a pre-grooming meeting | Pre-grooming
Defect - Non-Prod | Defect out of one of the stories above or during testing | QA to open, BA to assure properly defined, groomed, etc. | Pre-grooming (meeting if necessary) | Should be in current iteration and under a user story
Defect - Prod - Non-critical | There is an acceptable work around and deemed not necessary to fix right away. | Should be put in current iteration for discussion by the person in rotation, likely prior to being categoried as "non-critical". Cherwell ticket number should be included in the title. If not from Cherwell, email chain should be added as an attachment. Severity should be assigned. BA to assure above tasks are performed. | Pre-grooming/Grooming
Defect - Prod - Critical | Has to be fixed right away. i.e. comes in as Cherwell ticket marked as SEV 4 or higher, end user alerts team directly, or discovered by team. | Should be put in current iteration for discussion by the person in rotation. Cherwell ticket is required, Rally defect is required. Cherwell ticket number should be included in the title. If not from Cherwell, email chain should be added as an attachment. Severity should be assigned. BA to assure above tasks are performed.
Transformer Failure - Data Fix | Comes in as a Cherwell ticket, has "Transformer" in the description
Cross Train - Corrective action or support
Cross Train - for future assigned development work
Process Improvement
Prod Validations
Environment Impact Tests
Infrastructure Mandate, External Interface Changes | i.e. TLS
Spikes | research or analysis for another story
Technical Stories | Introduced by a developer for development or QA to understand what is being developed and how. References another user story
Technical Debt | Does not reference another user story. i.e. maintenance, certificate updates, developer access
Technical Defect | Is one of the other defect categories but requires technical documentation. Should require a RCA. Not UI driven.
Troubleshooting | Could turn into a defect but to capture the time for looking into it
TODO
Message server Cherwell descriptions